## Sample Housing Element Timeline
Bay Area Housing Element Update | 2021 | [11 empty] | 2022 | [11 empty] | 2023
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Start process | bar: 2021 Jan to 2021 Mar
Develop and initiate engagement strategy* | bar: 2021 Mar to 2023 Jan
• Brief Council and/or Planning Commission | bar: 2021 Feb to 2021 Mar
• Kickoff public meeting | bar: 2021 May
Complete initial research/key trends | bar: 2021 Mar to 2021 May
Identify scale of rezoning needed | bar: 2021 Jun to 2021 Aug
Rezoning and associated CEQA work | bar: 2021 Sep to 2022 May
Complete programs/policies | bar: 2022 Jan to 2022 Feb
Prepare draft plan | bar: 2022 Mar to 2022 May
Initial public hearings | bar: 2022 May to 2022 Jun
Review by California Housing & Community Development | bar: 2022 Jul to 2022 Aug
Revise plan if needed | bar: 2022 Sep to 2022 Oct
Hold adoption public hearings | bar: 2022 Oct to 2022 Nov
Complete Housing Element | bar: 2022 Oct to 2022 Nov
Submit for State certification | bar: 2022 Nov
* This schedule assumes a robust community engagement strategy with stakeholder and public meetings throughout. ** Additionally, this timeline builds in two months of time before the January 2023 deadline.

## AFFH Tasks
Bay Area Housing Element Update | 2021 | [11 empty] | 2022 | [11 empty] | 2023
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Start process | bar: 2021 Jan to 2021 Mar
Develop and initiate engagement strategy* | bar: 2021 Mar to 2023 Jan
Convene Equity Advisory Committee, create fair housing outreach plan, and engage for input and feedback at each AFFH step | bar: 2021 Aug to 2021 Nov
Brief Council and/or Planning Commission | bar: 2021 Feb to 2021 Mar
Brief Council and/or Planning Commission about new AFFH requirements and guidance | bar: 2021 Jul to 2021 Aug
Kickoff public meeting | bar: 2021 May
Complete initial research/key trends | bar: 2021 Mar to 2021 May
Complete Assessment of Fair Housing | bar: 2021 Aug to 2021 Oct
Identify scale of rezoning needed | bar: 2021 Jun to 2021 Aug
Assess fair housing implications of identified sites to accomodate RHNA | bar: 2021 Nov to 2021 Dec
Rezoning and associated CEQA work | bar: 2021 Sep to 2022 May
Identify and prioritize 4-6 contributing factors to the fair housing issues identified in the assessment | bar: 2022 Jan
Complete programs/policies | bar: 2022 Jan to 2022 Feb
Define fair housing goals, policies and actions | bar: 2022 Jan
Prepare draft plan | bar: 2022 Mar to 2022 May
Initial public hearings | bar: 2022 May to 2022 Jun
Review by California Housing & Community Development | bar: 2022 Jul to 2022 Aug
Revise plan if needed | bar: 2022 Sep to 2022 Oct
Hold adoption public hearings | bar: 2022 Oct to 2022 Nov
Complete Housing Element | bar: 2022 Oct to 2022 Nov
Submit for State certification | bar: 2022 Nov
* This schedule assumes a robust community engagement strategy with stakeholder and public meetings throughout. ** Additionally, this timeline builds in two months of time before the January 2023 deadline.

## Other Key Datess
Bay Area Region RHNA 6 Housing Element Update
Key Dates
2021
January 21, 2021 | The ABAG Executive Board approved Draft RHNA Methodology; ABAG sends methodology to State for review.
Spring 2021 | ABAG issues Draft RHNA allocations to jurisdictions.
April 1, 2021 | Annual Progress Reports due, even during Housing Element years.
Summer/Fall 2021 | ABAG conducts RHNA appeals.
Late 2021 | ABAG issues Final RHNA allocations to jurisdictions.
2022
April 1, 2022 | Annual Progress Reports due, even during Housing Element years.
June 30, 2022 | Pipeline Projects Deadline -- If a project receives its Certificate of Occupancy before this date, it cannot count towards the 2023-2031 Housing Element.
2023
Final deadline - January 2023 | Housing Elements must be adopted by City Councils or Board of Supervisors by this date. Jurisdictions can adopt their zoning changes before they adopt their housing element or at the same time as they adopt their housing element.
The timeline chart on the prior page builds in two months of time before the January 2023 deadline.
Approximately May 2023 | Approximtely four months after the January 2023 deadline, potential penalties if the Housing Element is not complete and adopted.
2026
Spring 2026 | Programs to Rezone Deadline -- If a jurisdiction does not have the sites to satisfy their RHNA, they must develop a Program to Rezone. While jurisdictions lose significant flexibility (e.g., zoning must be by-right), jurisdictions can have more time to complete the rezoning.