## Sample Housing Element Timeline
Bay Area Housing Element Update | 2021 | [11 empty] | 2022 | [11 empty] | 2023
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Start process | bar: 2021 Jan to 2021 Mar
Develop and initiate engagement strategy* | bar: 2021 Mar to 2023 Jan
• Brief Council and/or Planning Commission | bar: 2021 Feb to 2021 Mar
• Kickoff public meeting | bar: 2021 May
Complete initial research/key trends | bar: 2021 Mar to 2021 May
Identify scale needed rezoning | bar: 2021 Jun to 2021 Nov
Rezoning and associated CEQA | bar: 2021 Sep to 2022 May
Complete programs/policies | bar: 2022 Jan to 2022 Feb
Prepare admin and draft plan | bar: 2022 Jan to 2022 Apr
30 day public comment period and 10 day review period | bar: 2022 Apr
Comission and Council Hearings | bar: 2022 Apr to 2022 May
Review by California Housing & Community Development | bar: 2022 Jun to 2022 Aug
Revise plan if needed | bar: 2022 Sep to 2022 Nov
Hold adoption public hearings | bar: 2022 Nov to 2022 Dec
Complete Housing Element | bar: 2022 Nov to 2022 Dec
Submit for State certification | bar: 2022 Dec
* This schedule assumes a robust community engagement strategy with stakeholder and public meetings throughout. ** Additionally, this timeline assumes the Housing Elements will be submitted one month before the deadlne.

## Other Key Dates
Bay Area Region RHNA 6 Housing Element Update
Key Dates
2021
January 21, 2021 | The ABAG Executive Board approved Draft RHNA Methodology; ABAG sends methodology to State for review.
Spring 2021 | ABAG issues Draft RHNA allocations to jurisdictions.
April 1, 2021 | Annual Progress Reports due, even during Housing Element years.
Summer/Fall 2021 | ABAG conducts RHNA appeals.
Late 2021 | ABAG issues Final RHNA allocations to jurisdictions.
2022
April 1, 2022 | Annual Progress Reports due, even during Housing Element years.
June 30, 2022 | Pipeline Projects Deadline -- If a project receives its Certificate of Occupancy before this date, it cannot count towards the 2023-2031 Housing Element.
Spring 2022 | Jurisdictions must make the first draft revision of the housing element available for at least 30 days for comment. If any comments are received, they must take at least 10 additional business days to consider and incorporate public comments. The jurisidictions must then post any subsequent draft revision on its internet website and to email a link to the draft revision to individuals and organizations that have requested notices relating to the local government’s housing element, as specified. This revised draft can then be submitted to HCD for review.
Summer 2022 | HCD has 90 days to review the draft Housing Element annd report its written findings to the planning agency within 90 days of receiving the first draft submittal for each housing element revision or within 60 days of its receipt for a subsequent draft amendment or adoption.
2023
Final deadline - January 15, 2023 | Housing Elements must be adopted by City Councils or Board of Supervisors by this date. Jurisdictions can adopt their zoning changes before they adopt their housing element or at the same time as they adopt their housing element.
The timeline chart on the prior page builds in one month of time before the January 2023 deadline.
Approximately May 2023 | Approximtely four months after the January 2023 deadline, potential penalties if the Housing Element is not complete and adopted.
2026
Spring 2026 | Programs to Rezone Deadline -- If a jurisdiction does not have the sites to satisfy their RHNA, they must develop a Program to Rezone. While jurisdictions lose significant flexibility (e.g., zoning must be by-right), jurisdictions can have more time to complete the rezoning.