## Slide 1: Primer for how to use this resource
Staff Introduction/Instructions to Roadmap
      Family-owned/operated farm applicants will likely not be development savvy. This roadmap can help applicants avoid repeated trips to the planning desk.
      Tailor the following template by identifying the materials, and state, local and regional approvals needed to get farmworker housing approved in your jurisdiction.
      This process map can serve as an informational tool to help your applicants make strategic decisions about timing of work and feasibility of their project before they invest.
***Anything in a yellow highlight is an area that we recommend customizing for your jurisdiction’s rules and regulations***

## Slide 2: Introduction/Overview
Are you a property owner/farm owner considering building housing for your workers?*
“Farmworkers are traditionally defined as people whose primary incomes are earned through permanent or seasonal agricultural labor. Farmworkers are generally considered to have special housing needs due to their limited income and the often unstable nature of their employment.”
– California Department of Housing and Community Development**
What is farmworker housing?
Farmworker housing is defined as housing units that are occupied by farmworkers and their immediate family members. This housing may or may not be occupationally restricted to farmworkers.
Are you interested in building farmworker housing?
You might be a:
Farm Owner/Operator who wants to build housing for your employees
Property Owner who has agriculturally-zoned land that you want to develop
Affordable housing developer interested in exploring farmworker housing
Why is farmworker housing important?
A safe and secure food supply requires a healthy, trained and stable workforce living in quality affordable housing.
*Some definitions of farmworker include small-scale farm operators.
**Agricultural Employee/Farmworker Definition: An agricultural employee, operator, or owner primarily engaged in an agricultural operation. This definition differs by jurisdiction, but usually includes ranching and dairy.
Farmworker Housing Development Roadmap

## Slide 3: Common Pitfalls
Farmworker Housing Development Roadmap
This resource is designed to provide an overview of the development process for farmworker housing and to highlight areas for property owners to save time and money.
STEP 1
Pre-Application Process
STEP 2
Planning and Environmental Review
STEP 3
Building Permit Application & Approval
  POTENTIAL BARRIERS
Sewer/Water Access: Does your site have access to water and sewer? For most farmworker housing projects, an on-site water treatment system (OWTS) will be required. More information in next slides.
State Oversight: Building 5+ units may require an employee housing permit as well as approval to extend water/sewer services
  POTENTIAL BARRIERS
Zoning Approval Process: Review your jurisdiction’s zoning code and ask your Planning Department what the approval process for farmworker housing is. If your development requires a period of public comment, please anticipate additional time.
  POTENTIAL BARRIERS
Multi-departmental Review: In addition to the Planning and Environmental department, your project may be reviewed by additional departments. Anticipate an appropriate timeline.
Save Money & Time on Construction: Consider exploring manufactured or pre-built homes early in the process.

## Slide 4: Milestone Roadmap
A standard farmworker housing project usually requires three steps of approval:
STEP 1
Pre-Application Process
Initial meeting with Planning department to review proposed development
Initial conversations with Environmental Health department
Note: This resource is designed to help people who are interested in farmworker housing understand major hurdles and barriers early in the development process.
This roadmap also clarifies local and state considerations for farmworker housing.
STEP 2
Planning and Environmental Review
Submit application to Planning Department
Review by applicable agencies
Edits & Resubmission (if applicable)
Public Hearing (if applicable)
Planning Permit Approval
STEP 3
Building Permit Application & Approval
Share building permit application with other applicable agencies for their review
Additional Edits & Resubmission (if applicable)
Building Permit Approval
Construction & Inspection
Bolded steps have additional information on the following pages.

## Slide 5: Detailed Roadmap STEP 1: Pre-Application Process
Check your jurisdiction’s requirements related to farmworker housing. Schedule a pre-approval meeting or consultation with your Planning Department and Environmental Health Department. [Insert links or update department names as needed] Consider the following as you prepare for your meeting:
Planning Department
Initial meeting with Planning department to review proposed development
Environmental Health Services
Initial conversations with Environmental Health department
# of Units: How many units do you want to build?
1 unit
Consider building an Accessory Dwelling Unit (ADU) if you have a property that has an existing home.
[Link to your jurisdiction’s ADU policy/program]
2-5 units
Check if your local ordinance has a streamlined approval process for small-scale permanent agricultural employee housing (usually less than 5 units) (see Template Zoning Ordinance)
5+ units
If you construct more than 5 units, note that you may encounter additional oversight hurdles at the state level as you seek water and sewer options in your application.**
Additional considerations for early pre-application stages on next slide.
**A water supply for any development consisting of five or more service connections is classified as a “small state water system” and water supply to a project serving 25 or more people per day, for at least 60 days per year, is classified as a “public water system.” Both water system classifications trigger oversight authority by your Regional Water Quality Control Board, which would require an attempt to obtain a connection from an urban service area prior to considering an application. For most farmworker housing projects, an on-site water treatment system (OWTS) will be required. Additionally, if housing 5+ farmworkers, you will need to obtain an Employee Housing Permit from California HCD.
[Yellow highlighted areas are for recommended customization and edits to make this template specific to your jurisdiction.]

## Slide 6: Detailed Roadmap STEP 1: Pre-Application Process
Check your jurisdiction’s requirements related to farmworker housing and revise the following. Schedule a pre-approval meeting or consultation with your Planning Department and Environmental Health Department. Consider the following as you prepare for your meeting:
Planning Department
Initial meeting with Planning department to review proposed development
Environmental Health Services
Initial conversations with Environmental Health department
Zoning: What is permitted on your parcel?
What is your parcel zoned for?  Based on your jurisdiction’s zoning code and State law, projects that meet certain requirements may be expedited. [Revise and add zoning specifications] ***
If your parcel is protected by any conservation easements or the Williamson Act?  Inquire about any additional paperwork needed to build farmworker housing on your protected land.*^
Does your site have an on-site water treatment system (OWTS)?
If not, how do you plan to address water and sewer needs?
  Connection to an urban service area
  Construct OWTS
Water & Sewage
Additional Considerations
Permanent or Temporary Development
Maximum Development Size & Minimum Lot Size
Design Requirements
Floodplain: Use FEMA’s flood maps to check if you are in a floodplain, which could make development difficult or impossible
Access to publicly-maintained road
NOTE: Check with your Environmental Health Department representative to understand water and sewage requirements for your project. Understanding your options for water and sewage and having a cost range in mind early on may save you time and money.
***California State Law: California Health and Safety Code Sections 17021.5 and 17021.6 adopted in 2013 require agricultural employee housing to be permitted by-right, without a conditional use permit (CUP), in single-family zones for six or fewer persons and in agricultural zones with no more than 12 units or 36 beds. Please check your local jurisdiction’s planning code to see how they permit employee housing and if there are additional local zoning regulations that you need to consider.
*^According to California State Assembly Bill 1505, farmworker housing is a compatible use on Williamson Act Land.

## Slide 7: Detailed Roadmap STEP 2 : Planning and Environmental Review
Check your jurisdiction’s requirements related to farmworker housing and revise the following. Based on your initial consultation, prepare your application for the Planning Department. After you submit your application, your proposed project may undergo the following approval process:
Planning Department
Submit application to Planning Department
Environmental Health Services
Review by applicable agencies
Edits & Resubmission (if applicable)
Public Hearing (if applicable)
Planning Permit Approval
Sample Planning Permit Application Materials
[Please customize this checklist to your jurisdiction. The below checklist is based off the San Mateo County Farm Labor Housing Guidebook.]
Planning Permit Application Form & Checklist
Farmworker Housing-Specific Application
Coastal Development Permit Application, if applicable
Agricultural District/Conservation District Permit Application, if applicable
Use Permit, if required
Grading Permit Application, if required
Environmental Information Disclosure Form
Proof of Ownership (copy of deed/tax bill)
Well pump test and water quality results, if applicable
Drawings, including :
  Scaled site plan depicting parcel boundaries, easements, existing and proposed structures, access, driveways, water lines, storage tanks, septic tanks and leach fields, location and type of existing agriculture
  Floor plans
  Utility Plan, including conceptual on-site wastewater treatment system design, if applicable)
  Grading and Drainage Plan
  Erosion Control Plan
  Driveway/Access Plan

## Slide 8: Detailed Roadmap STEP 2 : Planning and Environmental Review
Check your jurisdiction’s requirements related to farmworker housing and revise the following. Based on your initial consultation, prepare your application for the Planning Department. After you submit your application, your proposed project may undergo the following approval process:
Planning Department
Submit application to Planning Department
Environmental Health Services
Review by applicable agencies
Edits & Resubmission (if applicable)
If the site is not already connected to water and sewer service, many farmworker housing projects will require an Onsite Wastewater Treatment System (OWTS). During the planning permit review process, the Environmental Health Department will look for a sufficient water and sewage system.
[Insert additional requirements]
NOTE: [Insert any deed restriction or affidavit restrictions stating that this housing will only be used for farmworkers]
Public Hearing (if applicable)
Based on your Planning Department’s zoning requirements for farmworker housing, your project may be approved through a planning clearance or special permit, which would eliminate the need for a public hearing.*
[Insert jurisdiction information on specifics (i.e. unit size) that might lead to a public hearing and how long that would take]
Planning Permit Approval
*A planning clearance is usually an administrative approval from the Planning Department. A special permit is subject to the specific provisions of your jurisdiction’s planning process. Both a planning clearance and special permit do not require a public hearing. See Template Zoning Ordinance for more information.
[Yellow highlighted areas are for recommended customization and edits to make this template specific to your jurisdiction.]

## Slide 9: Detailed Roadmap STEP 3: Building Permit Application & Approval
After you obtain your planning permit, prepare your application for your building permit.
Planning, Environmental Health, Buildings, Public Works, Fire Authority, [Add additional departments]
Share building permit application with other applicable agencies for their review
Additional Edits & Resubmission (if applicable)
Your application may be reviewed by subject matter experts, including but not limited to, Planning, Environmental Health, Buildings, Public Works, the Fire Authority, and [Insert additional departments].
Your review may consist of zoning, building code, water supply/onsite wastewater treatment systems, seismic/soil stability, drainage and grading, fire safety/access, [Insert additional requirements].
NOTE: If housing 5+ farmworkers, you will need to obtain an Employee Housing Permit from California HCD.
Buildings
Building Permit Approval
Buildings
Construction & Inspection
NOTE: Consider opportunities to use manufactured or pre-built homes to save time and cost on construction.
[Yellow highlighted areas are for recommended customization and edits to make this template specific to your jurisdiction.]

## Slide 10: Detailed Roadmap STEP 3: Building Permit Application & Approval
After you obtain your planning permit, prepare your application for your building permit.
Planning, Environmental Health, Buildings, Public Works, Fire Authority, [Add additional departments]
Share building permit application with other applicable agencies for their review
Additional Edits & Resubmission (if applicable)
Buildings
Building Permit Approval
Buildings
Construction & Inspection
Sample Building Permit Application Materials
[Please customize this checklist to your jurisdiction. The below checklist is based off the San Mateo County Farm Labor Housing Guidebook.]
Building Permit Application Form
Development Plans
Complete on-site wastewater treatment system design, if applicable
Stormwater Review Form
[Yellow highlighted areas are for recommended customization and edits to make this template specific to your jurisdiction.]

## Slide 11: Additional Resources
Water & Sewage Guidance (before you start)
Building in rural, unincorporated areas can be difficult and have unexpected costs because of water and sewage requirements. However, we hope that this does not discourage you from pursuing this project.
[Insert your jurisdiction’s specific programs and guidance related to OWTS
Are you looking for additional funding for your project?
Check if your jurisdiction has any specific funds available for farmworker housing projects
California HCD Joe Serna Jr. Farmworker Housing Grant Program
USDA Section 514 and 516 Loan and Grant Program
[Insert potential funding sources specific to your jurisdiction for farmworker housing]
[Yellow highlighted areas are for recommended customization and edits to make this template specific to your jurisdiction.]

## Slide 12: Additional Resources
FAQs
Q: Do I have to be a farm operator to build farmworker housing?
A: No, anyone can build farmworker housing and most jurisdictions do not require farmworker housing to be on the same site as the agricultural operation.
Q: Can my property be occupied by tenants who are not farmworkers?
A: There are examples of larger-scale housing developments that have a set-aside for farmworker units. For smaller-scale developments, [Please double check with your Planning Department and any external funding sources you may have received to understand any tenant requirements and related tenant employment verification processes].
Q: Who I contact with follow-up questions?
A: [Insert jurisdiction point of contact]
Q: [Space to insert jurisdiction-specific FAQ]
A:
Q: [Space to insert jurisdiction-specific FAQ]
A:
[Yellow highlighted areas are for recommended customization and edits to make this template specific to your jurisdiction.]